## Sheet1
Neighbourhood Plan
Action Minutes from meeting held 3rd September 2013 @ 7pm
Present: N Oldbury (Chair), P Douglas, J Douglas, D Askew, P Millar, N Cockrell & James (BDC) W Davies (Clerk)
Apologies from D Pell and B Woodcock
| Items | Issues | Actions
1 | Review NP Progress
Stage 1
| Subdivison of Responsibilities | PD read through the project plan that Helen used and stage 1 is on track;
however the group has not took on indiviual responsibilities. PD is doing a lot of paper chasing for the paper trial.
Stage 2
| Sustainability Assessment | Still to carry out | Pending untill policies have been written - should be done before the end of stage 2
| Character Assessment | Help needed to write up the Assessment | James as agreed to help with the Assessment and to be paid with the NP funding.
| SWOT analysis | SWOT Analysis needs writing up | PD will do a draft analysis for the next meeting
| Landowners | No reponse from the letters sent to local businesses | NC to give PD letters to resend out to Businesses & Landowners and invite them to a drop in session. If the landowners rent their land then there is the difficulty of finding out details of the farmers; still to contact 3 landowners.
| LPA Support | LPA is supporting with providing the maps and mapping out of key sites. | NC to speak with Jo - replotting the business map
|  | Need to review planning policies | Planning Aid to help with
|  | Any mapping contraints | NC - BDC has this information
|  | Review any current planning applications | NC - BDC has this information
| Website (History) | A write up of the History of Elkesley is required | PD is looking at some information and will draft it up
| Second Consultation | Review of information from the second consultation | The 2nd consultation went well and PD took another map and sports and leisure was highlighted. Following the consultation on the 21st September the group will be able to pull all stage 2 together.
| Group Questionnaire | Distribution of group questionnaires | PM to take to the Action Group
|  |  | PD to take to the Physic | ?
JD to take to the playgroup
|  |  | ? To take to the Zumba | ?
PD to take to the Memorial Hall Committee and bingo group
WD to take to the Parish Council
DA to take to the Boules Group
JD to take to the Elkesley Playground Committee
BW to take to the Primary School and Governors
NO to take to the football club
| Children's Competition | Involvement of Primary School and Tuxford School children | fliers have been done for the Tuxford children - JD PD to hand out at bus stop. Primary school children are drawing posters etc to be judged on the 21st September.
The Retford Times are attending the event on the 21st September.
Stage 3
| Generation of Options |  | Not able to do till after the next meeting
| Draft outline structure of Plan |  | Not able to do till after the next meeting
| External Support (Funding) |  | Not able to do till after the next meeting
2 | Stage 4
| Summary Plan to every household |  | To discuss at the next meeting
| Consultation Event (December) |  | To discuss at the next meeting
3 | Consultation Event 21st Sept
|  | Kids competition - judges | Neil, Natalie and Mr Barker
|  | Activities | Wellie wanging, boules, hula hoops, skittles,football shoot out,tyres
|  | Food | Debbie & Geoff - BBQ and drinks
|  | Flyers | To be distributed - volenteers required
4 | Budget/funding |  | WD produced expenses todate
5 | Any other business |  | None
6 | Date of next meeting | 1st October 7pm at the Hall | WD to book Hall